| WORK PROGRAM COVER SHEET |
| --- |
| Name and Address of Contractor: | Village of Piermont |
| Federal Tax ID number: | 14-6002371 |
| Title of Project: | Local Waterfront Revitalization Program Update: Planning for the Post Sandy World |
| Grant application number: | 40651 |
| Contract number: | T1000545 |
| Department liaison: | Lisa Vasilakos |
| Community contact: | Christopher Sanders, Mayor |
| Community contact address: | Village of Piermont 478 Piermont Avenue Piermont, NY 10968 |
| Telephone number: | 845-359-1258 |
| Fax number: | 845-359-0466 |
| Email: | csanders@piermont-ny.org |
| Department reviewer: | Kenneth Smith |

ATTACHMENT B-1 – EXPENDITURE BASED BUDGET

| A. Salaries |  | $0.00 |
| --- | --- | --- |
| B. Travel |  | $0.00 |
| C. Supplies |  | $0.00 |
| D. Equipment |  | $0.00 |
| E. Contractual Services |  | $35,000.00 |
| F. Other |  | $39,650.00 |
| TOTAL PROJECT COST |  | $70,000.00 |
| Total State Funds |  | $35,000.00 |
| Total Local Share |  | $35,000.00 |

| A. SALARIES (including fringe benefits) |
| --- |
| Title | Annual Salary | Amount Charged to Project |
| SUBTOTAL | $0.00 |

| B. TRAVEL |
| --- |
| SUBTOTAL | $0.00 |

| C. SUPPLIES |
| --- |
| SUBTOTAL | $0.00 |

| D. EQUIPMENT |
| --- |
| SUBTOTAL | $0.00 |

| E. CONTRACTUAL SERVICES |
| --- |
| Professional planning services for the development of LWRP update……………………………..$35,000.00 Subcontractor: To be determined. |
| SUBTOTAL | $35,000.00 |

| F. OTHER |
| --- |
| Planning and Project Administration Services-InKind and Cash $39,650 LWRP Section Committees (Pier, Business District, Waterfront, Upland Areas, Sparkill Creek and Marsh Areas) and Waterfront Advisory Committee -25 people for 80 hours @$15/hr = $30,000 ; Professionals Serving as Volunteers on Waterfront Comm(2) - @$120/hr for 15 hours = $3,600, Grants Administration -50 hours @$55/hr=$2,750 (cash);Waterfront Resiliency Commission Work on LWRP-Related Planning – 5 people for 24 hours @$15/hr=$1,800; Legal, Accounting and Audit = $1.500 (cash) |
| SUBTOTAL | $39,650.00 |

ATTACHMENT C - WORK PLAN

| Contractor: | Village of Piermont |
| --- | --- |
| Contract Number: | T1000545 |
| Program Contact Person: | Christopher Sanders, Mayor |
| Phone: | 845-359-1258 |
| Fax: |  |
| Email: | csanders@piermont-ny.org |

Local Waterfront Revitalization Program Update: Planning for the Post Sandy World

1.	Project Description

The Village of Piermont will update its 1992 Local Waterfront Revitalization Program. The Program will build on the current development of a Waterfront Adaptation Vision Plan and Resiliency Roadmap and will focus on strategies that reduce risk to infrastructure and property from sea level rise, revitalize the economy and conserve coastal resources.

This project involves the preparation of a Local Waterfront Revitalization Program pursuant to the provisions of New York State Executive Law, Article 42, for the Village of Piermont.  Completion of this project may integrate preparation of a harbor management plan as set forth in 19 NYCRR Part 603 and further described in guidelines prepared by the Department of State.

The Village of Piermont is located on the Hudson River and has approximately 2.5 miles of shoreline.  The Village will identify strategies that focus on economic development, sea level rise and storm surge protection measures.

2.	Project Attribution and Number of Copies

The Contractor must ensure that all materials printed, constructed, and/or produced acknowledge the contributions of the Department to the project.  The materials must include the Department of State logo and the following acknowledgment:

"This (document, report, map, etc.) was prepared for the New York State Department of State with funds provided under Title 11 of the Environmental Protection Fund Act."

The Contractor must submit to the Department all required products, clearly labeled with the NYS Comptroller's Contract # as indicated on the Face Page of this contract and where applicable, the related Task # from this Work Plan.  The Contractor shall submit:

- Draft products: two paper copies of each product. In addition, all draft products must be submitted as an electronic copy in Word or Word Perfect and Adobe Acrobat Portable Document Format –PDF (created using 300 dpi scanning resolution).

- Final products: two paper copies of each product.  In addition, all final products (including reports, designs, maps, drawings, and plans) must be submitted as an electronic copy in Word Perfect or Microsoft Word and Adobe® Acrobat® Portable Document Format - PDF (created using 300 dpi scanning resolution) and be submitted on a labeled CD-R type CD.  The CD must be labeled with the contractor name, the Departments contract #, and project title.

- Electronic data for all Geographic Information System-based mapping products must be included in either ArcGIS format, or similar product acceptable to the Department, and comply with the requirements for Contract GIS Products.

- Electronic data for all designs, drawings, and plans must be submitted in the original software that they were created (such as CAD format or other similar product acceptable to the Department) as well as in JPEG or GIF format.

- Pictures and photographs must be dated and captioned with the location and a brief description of the activity being documented. Electronic data for all pictures and photographs must be submitted in JPG or GIF format or other similar product acceptable to the Department.

The contributions of the Department must also be acknowledged in community press releases and other notices issued for the project, including web site postings and other forms of digital distribution.   Project press releases and other notices shall be submitted to the Department for review and approval prior to release, to ensure appropriate attribution.

3.	Compliance with Procurement Requirements

The municipal attorney, chief legal officer or financial administrator of the municipality shall certify in writing to the Department that applicable provisions of General Municipal Law were fully complied with.

4.	Project Components

[Note:  This work program can be edited to be appropriate for preparation of components of a Local Waterfront Revitalization Program or an amendment to an approved Local Waterfront Revitalization Program.]

Preparation of the Local Waterfront Revitalization Program (LWRP), including an integrated Harbor Management Plan (HMP), shall, at a minimum, involve the following tasks and provisions:

## Task 1:		Project Kick-Off Meeting

The Contractor, the Department, project partners and any other appropriate entities shall hold an initial meeting to review the project scope, project requirements, LWRP preparation requirements, roles and responsibilities of project partners and entities involved in preparing the LWRP, the selection process for procuring consultant services for the project, State Environmental Quality Review Act (SEQRA) compliance requirements, the schedule for submission of sections of the draft LWRP, the number of public meetings and techniques for public involvement proposed for the project, and any other information which would assist in project completion.  In addition, the composition of a Waterfront Advisory Committee shall be discussed during the project kick-off meeting.  The Contractor, or a designated project partner, shall prepare and distribute to all project partners a brief meeting summary clearly indicating the agreements/understandings reached at the meeting.  Work on subsequent tasks shall not proceed prior to Department approval of the proposed approach as outlined in the meeting summary.

Information on preparing a Local Waterfront Revitalization Program is contained in the Department's guidebook "Making the Most of Your Waterfront: Enhancing Waterfronts to Revitalize Communities" http://nyswaterfronts.com/communities_guidebooks.asp.

Products: 	Meeting held with appropriate parties.  Written meeting summary outlining agreements/understandings reached.

## Task 2:		Waterfront Advisory Committee

The Contractor shall establish a Waterfront Advisory Committee to oversee all aspects of the project in cooperation with municipal officials and the project consultant(s), if applicable.  The committee shall be representative of project stakeholders, including representatives of State, county, and municipal agencies with jurisdiction over project activities or the project area, and non-governmental and community based organizations.  A draft list of proposed members shall be circulated to the Department for review and approval prior to establishment of the committee.

Products:	Draft and final list of proposed members of project advisory committee.  Project advisory committee established.

## Task 3:		Request for Proposals (if applicable)

The Contractor shall draft a Request for Proposals (RFP) for consultant planning services, including a complete project description with site conditions, expected final results, a schedule for completion, and criteria for selecting a preferred proposal.  The Contractor shall submit the RFP to the Department for review and approval prior to release for solicitation of proposals.

Consultant services requested shall include all of the tasks, activities and responsibilities outlined in the "Project Components" section of this work program.

Products: 	Approved RFP released through advertisement in local papers, the New York State Contract Reporter, and other appropriate means.

## Task 4:		Consultant Selection and Compliance with Procurement Requirements

In consultation with the Department, the Contractor and an appropriate review committee shall review all proposals received as a result of the RFP.  At a minimum, the following criteria are suggested for use in evaluating consultant responses:

- Quality and completeness of the response.

- Understanding of the proposed scope of work.

- Applicability of proposed alternatives or enhancements to information requested.

- Cost-effectiveness of the proposal.

- Qualifications and relevant experience with respect to the tasks to be performed.

- Reputation among previous clients.

- Ability to complete all project tasks within the allotted time and budget.

Incomplete proposals that do not address all of the requested components should not be accepted for review and consideration.

For preparation/certification of final designs and construction documents, and for supervision of construction, a licensed professional engineer, architect or landscape architect licensed to practice in New York State is required.

The municipal attorney, chief legal officer or financial administrator of the municipality shall certify in writing to the Department that applicable provisions of General Municipal Law were fully complied with.

The Contractor's procurement record and consultant selection is subject to approval by the Department.

Products:	Consultant(s) selected and approved by the Department.  Written certification of compliance with procurement procedures.

## Task 5:		Subcontract Preparation and Execution

The Contractor shall prepare a draft subcontract or subcontracts to conduct project work with the consultant or consultants selected.  The subcontract(s) shall contain a detailed work plan with adequate opportunity for review at appropriate stages of project completion, a payment schedule (payments should be tied to receipt of products), and a project cost.  The subcontract(s) shall specify the composition of the entire consultant team, including firm name and area of responsibility/expertise, and those professionals from the consultant team or consulting firm that will be directly involved in specific project tasks.  The Contractor shall submit the draft subcontract(s) to the Department for review and approval, and shall incorporate the Department's comments in the final subcontract(s).  A copy of the final, executed subcontract shall be submitted to the Department.

Products:	Draft and final, executed consultant subcontracts.

## Task 6:		Second Project Meeting

In consultation with the Department, the Contractor shall hold a second project meeting with the consultant(s) and include the Waterfront Advisory Committee to review project requirements, site conditions, and roles and responsibilities; identify waterfront and harbor management planning issues, new information needs and next steps; and transfer any information to the consultant(s) which would assist in completion of the LWRP.  A decision will be made by DOS following this meeting, as to whether a harbor management plan will be necessary as part of the Local Waterfront Revitalization Program.  Project partners at this meeting will review the LWRP preparation process, including compliance with SEQRA, and identify SEQRA lead agency and involved agencies.  The Contractor or its consultant(s) shall prepare and distribute a brief meeting summary clearly indicating the agreements/understandings reached at the meeting.  Work on subsequent tasks shall not proceed prior to Department approval of the proposed approach as outlined in the meeting summary.

Products:	Project meeting held with appropriate parties.  Written meeting summary outlining agreements/understandings reached.

## Task 7:		Preparation of a Community Outreach Process and Plan

The Contractor or its consultant(s), the Waterfront Advisory Committee, and other partners as appropriate, shall prepare a method and process to encourage community participation in development and implementation of the LWRP.  At a minimum, the process shall include at least three public workshop type meetings to be conducted during the plan development.  The outreach plan shall identify key individuals, organizations, and entities to be involved, and shall identify the visioning process and the roles and responsibilities in coordinating the entire outreach process, logistics, and the proposed schedule of public meetings.  All public meetings will be publicized in the community through press releases, announcements, individual mailings, and any other appropriate means.  A summary of each public outreach session will be made available in written form and through other appropriate means, such as notices on the world wide web.  The outreach plan shall be submitted to the Department for review and approval.

Product:	Approved community outreach plan.

## Task 8: 		LWRP - Section I - Waterfront Revitalization Area Boundary

The Contractor or its consultant(s) shall prepare a narrative description and map of the waterfront revitalization area which includes surface waters and underwater lands.  The waterfront revitalization area should include those portions of the water body within the municipality, as well as adjacent upland which affects the water body through drainage, viewshed, and any other factors.  References to the Inventory and Analysis section justifying the inclusion of particular areas should be included in this section if beneficial for increased understanding.  The narrative must be accompanied by a boundary map.   Section I shall be submitted to the Department for review and approval.

Products:	Section I - Waterfront Revitalization Area Boundary, including narrative and map(s).

## Task 9: 	LWRP - Section II - Inventory and Analysis

The Contractor or its consultant(s) shall inventory and describe existing natural and built resources and conditions within the waterfront revitalization area including the harbor (which includes surface waters and underwater lands). (See Chapter 4 of the LWRP Guidebook.)  In addition, Section II must provide a thorough analysis of waterfront issues, opportunities, and constraints to development, and resource protection needs and a reasonable assessment of the vulnerable resources and potential risks associated with climate change.

Topics to be addressed include, but are not limited to, the following:

- Identification and assessment of existing land use and development

- Land use and ownership patterns (public and private), including underwater lands

- Abandoned, deteriorated, or underused sites and buildings

- Agricultural lands

- Identification and assessment of existing water-dependent uses and related issues

- Commercial, industrial, and recreational water-dependent uses (such as ferries, marinas, boat yards, transhipment facilities, swimming areas, vessel anchorage and mooring areas, commercial or recreational fishing or shellfishing areas and uses)

- Identification and assessment of existing zoning and other relevant local land use and development controls

- Zoning codes, subdivision review, site plan review, and design standards, etc.

- Identification and assessment of existing and desired open spaces, public access sites and recreational resources

- Identification and assessment of the condition of infrastructure

- water supply, stormwater and sewage treatment, vessel waste facilities, solid waste disposal, transportation systems, energy production and transmission,  bulkheads, docks and docking facilities and underwater infrastructure and structures, such as cables and pipelines

- Identification and assessment of historic and scenic resources

- National Register sites and districts, Scenic Areas of Statewide Significance, locally designated resources, and archaeological resources such as shipwrecks and historic dry docks

- Identification and assessment of natural resources, topography, hydrology, and geology

- NYS Significant Coastal Fish and Wildlife Habitat areas, locally important fish and wildlife habitats, wetlands, water courses, landscape features, steep slopes, minerals, etc.

- Assessment of issues related to water quality

- Point and non-point sources of pollution

- Water quality classification

- Assessment of issues related to flooding, erosion and other coastal hazards

- Assessment of issues related to navigation and dredging

- Summary of the existing authorities of federal, state, regional, and local agencies that have jurisdiction in the waterfront revitalization area.

  - the National Oceanic and Atmospheric Administration, the U.S. Coast Guard, U.S. Army Corps of Engineers, and the Department of Interior;

  - the State Departments of State, Environmental Conservation, Health and Transportation and the Offices of General Services and Parks, Recreation, and Historic Preservation;

  - agencies of the city, town, or village, or a county if the county regulates activities in the waterfront revitalization area;

  - the local harbormaster, bay constables, code enforcement officer, building inspector, police department or sheriff's office.

  - Section II shall be submitted to the Department for review and approval.

Products:	Section II - Inventory and Analysis with accompanying maps to depict the municipality's waterfront area resources, issues, and opportunities.

## Task 10:  	First Public Information Meeting

Following completion of the initial drafts of Section I - Waterfront Revitalization Area Boundary and Section II - Inventory and Analysis, the Contractor or its consultant(s) shall conduct a public information meeting regarding the identified local waterfront issues and opportunities and solicit public input regarding the completeness and accuracy of Sections I and II.

Products:	Public information meeting held.  Minutes of the public meeting.

## Task 12: 		LWRP - Section III - Local Waterfront Revitalization Policies

The Contractor or its consultant(s) shall refine applicable State waterfront revitalization policies to reflect local conditions and circumstances, including specific standards and proposed land and water uses for determining consistency with the policies.  Provisions of the State policies may be modified to correspond with local circumstances, but may not be diminished.  Section III shall be submitted to the Department for review and approval

Products: 	Section III - Local Waterfront Revitalization Policies.

## Task 13: 		LWRP - Section IV - Proposed Land and Water Uses and Proposed Projects

The Contractor or its consultant(s) shall describe and map proposed long-term land and water uses within the waterfront area, and proposed projects necessary to implement the LWRP.

Projects may include but not be limited to:

- Capital improvement or construction projects that are necessary to maintain or improve uses or conditions;

- Special studies, plans, design projects, or research necessary to advance or refine components of the LWRP;

- Projects to redevelop underused or deteriorated areas and sites,

- Projects to provide or improve public access;

- Projects to protect existing, or provide for new, water-dependent uses, such as marinas, boat yards, yacht clubs, port facilities, swimming beaches, or shellfishing; and

- Projects to enhance or restore wetlands and habitats.

Section IV shall be submitted to the Department for review and approval

Products:	Section IV - Proposed Land and Water Uses and Proposed Projects accepted by the Contractor and approved by the Department.

## Task 14:  	Second Public Information Meeting

Following completion of the initial draft of Section IV - Proposed Land and Water Uses and Proposed Projects the Contractor or its consultant(s) shall conduct a public information meeting regarding the identified local waterfront issues and opportunities and solicit public input regarding the completeness and accuracy of Section IV.

Products:	Public information meeting held. Minutes of the public meeting.

## Task 15: 		LWRP - Section V - Techniques for Local Implementation of the Program

The Contractor or its consultant(s) shall describe existing local laws and regulations, as well as any new or amended laws or regulations which are necessary to implement the policies, proposed uses, and projects set forth in Sections III and IV.  The Contractor or its consultant(s) shall draft such local laws and regulations as are necessary to implement the LWRP. Full drafts of new or amended laws and regulations, including a local consistency review law, should be in the appendix to the LWRP.

The Contractor or its consultant(s) shall also describe other public and private sector actions necessary to implement the LWRP, including actions by federal and state agencies necessary in order to fully implement and advance projects in the waterfront revitalization area.  These actions may include approving anchorage and mooring areas prior to designation, designating vessel waste no-discharge zones, dredging or maintaining major navigation channels and basins, constructing or maintaining breakwaters, funding certain studies, or providing technical assistance.

The Contractor or its consultant(s) shall also describe a local management structure for reviewing proposed waterfront projects for consistency with the LWRP, and the financial resources required to implement the LWRP.  Section V shall be submitted to the Department for review and approval.

Products:	Section V - Techniques for Local Implementation of the Program, and ALL drafts of any necessary amendments to existing laws or new local laws, including a local consistency review law.

## Task 16: 	LWRP - Section VI - Federal and State Actions and Programs Likely to Affect Implementation of the LWRP

The Department shall provide to the Contractor or its consultant(s) a generic list of federal and State agency actions and programs (Section VI. A.) which are to be undertaken in a manner consistent with the LWRP.  The Contractor or its consultant(s) shall describe specific federal and State actions (Section VI. B.) necessary to further implementation of the LWRP (technical assistance, funding, procedural changes, etc.).  Section VI shall be submitted to the Department for review and approval.

Products:	Section VI - Federal and State Actions and Programs Likely to Affect Implementation of the LWRP.

## Task 17: 		LWRP - Section VII - Local Commitment and Consultation

The Contractor or its consultant(s) shall describe the public consultation efforts undertaken in the preparation of the LWRP, such as public hearings, public informational meetings, and/or meetings with governmental agencies.  The Contractor or its consultant(s) shall also describe any local committees created to oversee preparation of the LWRP, as well as the role of other municipal agencies.  Section VII shall be submitted to the Department for review and approval.

Products:	Section VII - Local Commitment and Consultation.

## Task 18: 		Determination of Significance and Compliance with SEQRA

The Contractor shall request designation as Lead Agency for purposes of SEQRA.  The Lead Agency shall prepare, distribute and file a Full Environmental Assessment Form for purposes of evaluating the importance/significance of the impacts associated with preparing and adopting a LWRP.  Upon completing the Full Environmental Assessment Form, the Lead Agency shall make a Determination of Significance in accordance with the SEQRA regulations.  If the Determination of Significance results in a Positive Declaration, the Lead Agency shall prepare a Draft Generic Environmental Impact Statement for the Draft LWRP in accordance with State Environmental Quality Review Act (SEQRA) regulations and guidelines.  If the findings of the Determination of Significance are such that the LWRP will not have a significant adverse environmental impact, a Negative Declaration may be prepared and filed.  If a Negative Declaration is prepared and filed, then a Draft Generic Environmental Impact Statement will not be necessary and no further actions are necessary under the SEQRA regulations.  The Contractor or its consultant(s) shall determine whether a public hearing will be held on the Draft LWRP.  Completed SEQRA documents shall be submitted to the Department for review and approval.

Products:	Completed Full Environmental Assessment Form and associated SEQRA determination statements (Positive Declaration or Negative Declaration).  If the Determination of Significance results in a Positive Declaration, the Lead Agency, with the assistance of the consultant, shall prepare a Draft Generic Environmental Impact Statement for the Draft LWRP in accordance with State Environmental Quality Review Act (SEQRA) regulations and guidelines.  If a Draft Generic Environmental Impact Statement is prepared, a public hearing shall be held.

## Task 19: 		Draft LWRP

The Contractor or its consultant(s) shall submit a hard copy and electronic copy (.pdf format) of a complete Preliminary Draft LWRP document, with integrated harbor management, including a complete Draft Generic Environmental Impact Statement (if one is to be prepared), incorporating comments provided on each component section, to the Department for approval.  If revisions to the Preliminary Draft LWRP are needed, based on Department review, the Contractor or its consultant(s) shall make the required changes and resubmit the document to the Department for review.  All comments and requested revisions must be addressed to the satisfaction of the Department prior to advancing the document to 60-Day Review.

Following acceptance of the Preliminary Draft LWRP document by the Department, the Contractor shall formally accept the Draft LWRP as complete and ready for public review and authorize its submission to the Department for review by potentially affected State, Federal, and local agencies by resolution of the local municipal legislative body.  The Contractor or its consultant(s) shall also provide three (3) hard copies and one electronic copy (formatted in either Corel WordPerfect or Microsoft Word) of the Draft LWRP document to the Department.

Upon receipt of the required number of copies of the Draft LWRP (/Draft Generic Environmental Impact Statement, if applicable), the Department shall initiate a 60-Day Review by State, Federal, and other local agencies concurrent with the SEQRA review (if applicable).

Products:	(1) Preliminary Draft LWRP acceptable to the Department;  (2) a resolution of the local municipal legislative body accepting the Draft LWRP;  (3) the required number of copies of the Draft LWRP;  and (4) comments received as a result of Department initiated 60-Day Review.

## Task 20: 		Third Public Information Meeting

Following completion of the Draft LWRP and in conjunction with 60-Day Review, the Contractor or its consultant(s) shall conduct a public information meeting or meetings on the Draft Program.

Products:	Public meeting held.  Minutes of the public information meeting(s) and identification of changes to be made to the Draft Program as a result of the public meeting submitted to the Department for approval.

## Task 21: 		Final LWRP

Following the 60-Day Review of the Draft LWRP (/Draft Generic Environmental Impact Statement, if applicable), the Department shall meet with the Contractor or its consultant(s) to determine appropriate responses to all of the comments received; which shall be reflected in the Final LWRP document (and Final Environmental Impact Statement, if applicable) to the satisfaction of the Department.

The Contractor and/or its consultant(s) shall also submit a schedule of adoption to the Department of the LWRP and any local laws necessary for implementation of the LWRP.

Products:	Final LWRP (and Final Environmental Impact Statement, if applicable) and schedule of adoption.

Task 22:	MWBE Quarterly Reports

The contractor and its consultants and/or contractors shall submit MWBE Quarterly Reports (every March 31, June 30, September 30, and December 31) on the form provided, including a breakdown of payments issued to state-certified MWBE firms during the quarter.

Products:	MWBE reports submitted to DOS during the life of the contract.

Task 23: 	Project Status Reports

The Contractor or its consultant(s) shall submit project status reports semi-annually (every June 30 and December 31) on the form provided, including a description of the work accomplished, the status of all tasks in this work plan, schedule of completion of remaining tasks, and an explanation of any problems encountered.

Products:	Completed project status reports submitted to DOS during the life of the contract.

Task 24:	Final Project Summary Report and Measurable Results forms

The Contractor or its consultant(s) shall work with the Department project manager to complete the Final Project Summary Report and Measurable Results forms.  Final payment shall not be authorized until these forms have been completed and filed with project deliverables.

Products:	Completed Final Project Summary Report and Measurable Results forms submitted to DOS.

5.	Project Management Responsibilities

The Contractor shall administer the grant, execute a contract with the Department, and ensure the completion of work in accordance with the approved Work Plan.  Unless otherwise specified in the Project Description or under Project Components, the Contractor and/or its approved consultant(s) or subcontractor(s) shall conduct all work as described in the component tasks.

The Contractor:

- will be responsible for conducting all project work in conformance with the Work Plan included in the executed contract with the Department.

- will be responsible for all project activities including drafting request for proposals and managing subcontracts with consultants and subconsultants.

- will certify to the Department that the procurement record for project consultants and subcontractors complies with the applicable provisions of General Municipal Law.

- will receive approval from the Department for any and all consultant subcontracts before beginning project work.

- will be responsible for submission of all products and payment requests.

- will be responsible for coordinating participation and soliciting comments from local government personnel, project volunteers, and the public.

- will keep the Department informed of all important meetings for the duration of this contract.

- will receive approval from the Department before purchase of any equipment.

- will secure all necessary permits and perform all required environmental reviews.

- will ensure that all materials printed, constructed, and/or produced reflect the Department of State logo, feature the Secretary of State and the Governor, and acknowledge the contributions of the Department to the project.

- will ensure that all products prepared as a part of this contract shall include the NYS Comptroller's contract # as indicated on the Face Page of this contract.

- will ensure the project objectives are being achieved.

- will ensure that comments received from the Department and the project advisory committee, or other advisory group, are satisfactorily responded to and reflected in subsequent work.

- will recognize that payments made to consultants or subcontractors covering work carried out or products produced prior to receiving approval from the Department will not be reimbursed unless and until the Department finds the work or products to be acceptable.

The Department:

- will review and approve or disapprove of subcontracts between the Contractor and consultant(s) and any other subcontractor(s).

- will participate in project kick-off meeting and attend meetings that are important to the project.

- will review all draft and final products and provide comments as necessary to meet the objectives.

- must approve or disapprove any and all design, site plan, and preconstruction documents. Department approval must be obtained before construction may begin.

# Comments

Verify with community.